## Charter
ME 463 Senior Design
Project Title: | TerraProbe | Vision Statement: | Our vision is to revolutionize soil sampling and monitoring with an on-demand, portable, and labor/time efficient solution that delivers real-time analytics across different soil depths. TerraProbe should empower agricultural professionals and environmental researchers by providing accurate, data-driven insights to optimize crop yield, ensure soil stability, and enhance soil health management worldwide.
Team Name: | Down to Earth (D2E)
Team Members: | Sankaran Iyer, Lokesh Sriram, Chris Meyers, Jacob McKenrick, Avie Ghatge
Problem Statement (Current State) |  | Key Stakeholders (Role, Influence, Interest)
Soil sampling for agriculture, construction, and environmental research is labor-intensive, requires bulky equipment, and prone to contamination. Existing solutions are either manual, require significant time and effort, or are automated but bulky, expensive, and dependent on trained operators. Additionally, no current solution provides real-time soil analysis, as samples must be transported to laboratories for testing, delaying decision-making and increasing costs. There is a need for a portable, autonomous, and cost-effective soil sampling system that ensures accurate collection across multiple depth profiles and real-time analysis on salinity, mositure, NPK to improve efficiency and precision in soil assessment. |  | External stakeholders in the TerraProbe project include agricultural professionals and environmental researchers. Agricultural professionals (e.g., farmers and agronomists) will use TerraProbe for unmixed precise and multi-depth soil sampling. This can help them identify soil properties through device's real-time data on moisture, salinity, and temperature that determine/optimize crop yield, manage resources efficiently, and implement precision agriculture practices. The size and portability of TerraProbe are key advantages for farmers. Given that the device is compact and lightweight (under 25 kg), it is easy to carry, transport, and deploy across diverse agricultural fields, including small to medium-sized farms, making it ideal for conducting multiple soil samples without the need for heavy machinery or complicated setup.
Business / Society Benefit (Future State) |  | Project Scope
We envision the TerraProbe Soil Sampling Robot to be a portable and small-sized solution designed to dig soil without mixing and separate soil at different depths. Using a pinion and rack system, we ensure accurate sampling up to 18 inches deep with three distinct intervals. Unlike traditional methods that are labor-intensive, expensive, and lack real-time insights, TerraProbe offers a compact (≤ 25 kg) and cost-effective (<$600 prototype) solution.The robot also integrates real-time data sensors for moisture (±5% accuracy), salinity (±5%), and temperature (±1°C), delivering instant analytics via a user-friendly dashboard or web app. TerraProbe should surpass manual tools by eliminating human effort/labor and reducing sample contamination. It outperforms existing automated solutions by combining portability, real-time data collection, and affordability in a single device. Users gain instant soil condition reports, enabling informed decisions in precision agriculture and environmental monitoring. |  | IN Scope |  | OUT of Scope
|  | 1) Designing, Prototyping and Testing of Portable Soil Sampling Robot capable of Autonomous Operation. 2) Integration of sensor and Data Aquisition System measuring real-time data for soil properties (mositure, salinity, temperature, NPK). 3) Development of a user-friendly dashboard or WebApp for data visualization. 4) Cost effective design and production prototype (under $600/unit) |  | 1) Soil analysis beyond moisture, salinity, NPK, and temperature (ex. pH, nurtient levels) and advanced predictive analytics. 2) Diverse or extremely hard soil conditions (such as those suitable for construction land) 3) Mounting or attachment on vehicles
Key Milestones |  | Key Assumptions & Risks
Key milestones for the TerraProbe project include procuring essential materials, such as sensors, steel, and rack and pinion gears, followed by the manufacturing of the keyhole and casing. The next phase involves designing the DAQ system and dashboard to enable real-time data collection and visualization. Once completed, the assembly of the inner and outer casing, along with the integration of rack and pinion gears, will take place. Finally, the product will undergo rigorous testing across various soil types, including potting soil, soft clay, and hard dry soil, to ensure performance and reliability. |  | Key assumptions include that the pinion and rack system will generate sufficient force to navigate through soil types, particularly clay-like conditions, without compromising performance. Additionally, the stainless steel casing is expected to support the weight requirement while maintaining a lightweight design, crucial for portability. The system will also incorporate a separate handheld device for sensors, designed to be inserted into the soil, with the assumption that the soil conditions will generally be soft or clay-like for optimal sensor function. Risks associated with the project include potential issues with sensor accuracy, especially in varying soil types, and the possibility of sensor tip failure during use. Another risk is the challenge of competing with established market leaders who offer solutions for a wider range of soil conditions. Additionally, soil accumulation could impair the operation of the device over time, requiring frequent maintenance or design adjustments to ensure long-term reliability.
Team Members & Roles |  | Key Resources Required
Sankaran Iyer: Project Manager & Software Lead Avie Ghatge: Electronics & Components Lead Loki: Chief Engineer Chris: CAD & Modeling Lead Jacob: Sourcing, Materials & Design Lead |  | Machine Shop, E-Shop, Rack & Gear Assembly, Soil for Testing
Version: |  | Last Updated: