## 1. Scoring Matrix
For ME463, this scoring matrix has been defined for you. Reference it for accurate & consistent scoring of your risks, but do not modify it.
IMPACT
Score | PROBABILITY | Schedule | Budget | Product Requirements
HIGH | >25% | > 7 days | > $150 | Key requirements are significantly compromised.
MEDIUM | 11-25% | 4 - 7 days | $61 - $150 | Primary (key) requirements are partially compromised and/or secondary requirements are significantly compromised.
LOW | <10% | < 3 days | < $60 | Secondary requirements are partially compromised, but primary (key) requirements are not.

## 2. Risk Register
1. IDENTIFICATION | [5 empty] | 2. CURRENT ASSESSMENT |  |  |  | 3. TREATMENT |  | 4. RESIDUAL ASSESSMENT |  |  |  | 5. REVIEW, CONTROL, COMMUNICATE
ID | RAISED BY | DATE RAISED | CAUSE (IF…) | EFFECT (THEN…) | RISK OWNER | P | I | PI | Current Risk Score | STRATEGY | TREATMENT DESCRIPTION | P | I | PI | Residual Risk Score | Commentary | Last Updated
| The originator of the risk | When the risk was first identified | If uncertain event occurs due to (or because of) specified root cause(s). Tip: ask "why, why, why…" to drill down to root cause | then the ultimate impact to our objectives are. Tip: ask "so what, so what, …" | Single named owner | Probability of the event occurring | 'Worst' impact | DO NOT MODIFY | Calculated risk score | Select overall approach to treatment (Mitigate or Accept) | Summary of the treatment responses (actions, controls, fallbacks) that treat the risk. | Probability of the event occurring | 'Worst' impact | DO NOT MODIFY | Calculated risk score | Any additional notes, comments or actions | Enter the last review or update date for the risk
1 | Jacob McKenrick | 2025-02-02 | Machine tries to extract too much soil | Overloading lifting system |  | M | H | MH | 15 | Mitigate | Factor of safety of 3.0 used in design for the rack and pinion system | L | H | LH | 11 |  | 2025-02-02
2 | Jacob McKenrick | 2025-02-02 | Gear is improperly lubricated | Rack and pinion failure |  | M | H | MH | 15 | Mitigate | Provide guide on how often, and how to lubricate gears in rack and pinion system | L | H | LH | 11 |  | 2025-02-02
3 | Jacob McKenrick | 2025-02-02 | Soil gets lodged between teeth in the rack and pinion system | Rack and pinion jamming |  | H | M | HM | 14 | Mitigate | Cover rack and pinion as much as possible with machine frame to prevent liklehood of soil jamming | L | M | LM | 6 |  | 2025-02-02
4 | Jacob McKenrick | 2025-02-02 | Vibrations jeopardize structural integrity | Machine frame could damage or break |  | L | H | LH | 11 | Accept | Could use stronger material resistant to vibrations | L | H | LH | 11 |  | 2025-02-02
5 | Jacob McKenrick | 2025-02-02 | Wear on bearings | Bearing failure |  | M | M | MM | 10 | Mitigate | Design bearings for a large factor of safety | L | M | LM | 6 |  | 2025-02-02
6 | Jacob McKenrick | 2025-02-02 | Dirt, moisture, or calibration issues | Sensor malfunction |  | H | L | HL | 9 | Accept | Operator can always test samples several times to reduce error | H | L | HL | 9 |  | 2025-02-02
7 | Jacob McKenrick | 2025-02-02 | Short circuits or loose connections | Electrical Malfunction |  | M | M | MM | 10 | Mitigate | Ensure connections are strong and stable. Prevent wires from being exposed. | L | M | LM | 6 |  | 2025-02-02
8 | Jacob McKenrick | 2025-02-02 | Electomagnetic interference could influence data collection | Electrical Malfunction |  | L | M | LM | 6 | Accept | Operator can always test samples several times to reduce error | L | M | LM | 6 |  | 2025-02-02
9 | Jacob McKenrick | 2025-02-02 | Software errors | Incorrect Data Collection |  | L | L | LL | 1 | Accept | Double check software during testing | L | L | LL | 1 |  | 2025-02-02
10 | Jacob McKenrick | 2025-02-02 | Pinch points in rack and pinion system during extraction | Operator Injury |  | M | H | MH | 15 | Mitigate | Added limit switches as an Estop for rack and pinion system. Added safety covers over pinch points | L | M | LM | 6 |  | 2025-02-02
11 | Jacob McKenrick | 2025-02-02 | Instability of machine in soft soil | Machine could fall over |  | L | M | LM | 6 | Mitigate | Foot pedals added for operator to stand on to add stability to design | L | M | LM | 6 |  | 2025-02-02
12 | Jacob McKenrick | 2025-02-02 | Expelling of machine lubricant | Soil Contamination |  | L | M | LM | 6 | Accept | Look for more environmentally safe lubricant, use proper amount of lubricant | L | M | LM | 6 |  | 2025-02-02
13 | Jacob McKenrick | 2025-02-02 | Machine is loud | Noise Pollution |  | M | L | ML | 5 | Accept | Look into noise reduction or lubricant | M | L | ML | 5 |  | 2025-02-02
14 | [8 empty] | #N/A | [5 empty] | #N/A
15 | [8 empty] | #N/A | [5 empty] | #N/A
16 | [8 empty] | #N/A | [5 empty] | #N/A
17 | [8 empty] | #N/A | [5 empty] | #N/A
18 | [8 empty] | #N/A | [5 empty] | #N/A
19 | [8 empty] | #N/A | [5 empty] | #N/A
20 | [8 empty] | #N/A | [5 empty] | #N/A
21 | [8 empty] | #N/A | [5 empty] | #N/A
22 | [8 empty] | #N/A | [5 empty] | #N/A
23 | [8 empty] | #N/A | [5 empty] | #N/A
24 | [8 empty] | #N/A | [5 empty] | #N/A
25 | [8 empty] | #N/A | [5 empty] | #N/A
26 | [8 empty] | #N/A | [5 empty] | #N/A
27 | [8 empty] | #N/A | [5 empty] | #N/A
28 | [8 empty] | #N/A | [5 empty] | #N/A
29 | [8 empty] | #N/A | [5 empty] | #N/A
30 | [8 empty] | #N/A | [5 empty] | #N/A
31 | [8 empty] | #N/A | [5 empty] | #N/A
32 | [8 empty] | #N/A | [5 empty] | #N/A
33 | [8 empty] | #N/A | [5 empty] | #N/A
34 | [8 empty] | #N/A | [5 empty] | #N/A
35 | [8 empty] | #N/A | [5 empty] | #N/A
36 | [8 empty] | #N/A | [5 empty] | #N/A
37 | [8 empty] | #N/A | [5 empty] | #N/A
38 | [8 empty] | #N/A | [5 empty] | #N/A
39 | [8 empty] | #N/A | [5 empty] | #N/A
40 | [8 empty] | #N/A | [5 empty] | #N/A
41 | [8 empty] | #N/A | [5 empty] | #N/A
42 | [8 empty] | #N/A | [5 empty] | #N/A
43 | [8 empty] | #N/A | [5 empty] | #N/A
44 | [8 empty] | #N/A | [5 empty] | #N/A
45 | [8 empty] | #N/A | [5 empty] | #N/A
46 | [8 empty] | #N/A | [5 empty] | #N/A
47 | [8 empty] | #N/A | [5 empty] | #N/A
48 | [8 empty] | #N/A | [5 empty] | #N/A
49 | [8 empty] | #N/A | [5 empty] | #N/A
50 | [8 empty] | #N/A | [5 empty] | #N/A
Note on M1: The risk that remains after risk responses have been implemented.
Note on F3: The person responsible for monitoring the risk and for selecting and implementing an appropriate risk response strategy.
Note on K3: Mitigate - A risk response strategy whereby the project team acts to decrease the probability of occurrence or impact of a threat. Accept - Choosing to accept the risk (not mitigate) and will react only if & when it occurs.
Note on M3: Post treatment score
Note on N3: Post treatment score

## Ref. (hidden)
P/I | Strategy
L | Mitigate
M | Accept
H
Impact
Probability | LOW | MEDIUM | HIGH
HIGH | 9 | 14 | 20
MEDIUM | 5 | 10 | 15
LOW | 1 | 6 | 11
| Probability | Impact | PI | Score
| L | L | LL | 1
| L | M | LM | 6
| L | H | LH | 11
| M | L | ML | 5
| M | M | MM | 10
| M | H | MH | 15
| H | L | HL | 9
| H | M | HM | 14
| H | H | HH | 20