## Project Schedule
|  | A Down To Earth (D2E) Company |  |  | Project start: | [7 empty] | 2025-01-13
[5 empty] | Display week: | [7 empty] | 1
[5 empty] | PDR | [27 empty] | CDR | [27 empty] | FDR
[5 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16
[5 empty] | 1900-01-12 | [6 empty] | 1900-01-19 | [6 empty] | 1900-01-26 | [6 empty] | 1900-02-02 | [6 empty] | 1900-02-09 | [6 empty] | 1900-02-16 | [6 empty] | 1900-02-23 | [6 empty] | 1900-03-02 | [6 empty] | 1900-03-09 | [6 empty] | 1900-03-16 | [6 empty] | 1900-03-23 | [6 empty] | 1900-03-30 | [6 empty] | 1900-04-06 | [6 empty] | 1900-04-13 | [6 empty] | 1900-04-20 | [6 empty] | 1900-04-27
| TASK | START | END | time axis 1900-01-12 to 1900-05-03
 | time axis 1900-01-12 to 1900-05-03
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Preliminary Design Review - Initation
| Problem Definition | 1900-01-12 | 1900-01-15 | 4
| Market Analysis & Benchmark Research | 1900-01-15 | 1900-01-19 | 5
| Customer Requirements & Vision/Mission Statement | 1900-01-19 | 1900-01-21 | 3
| Member Roles & Resposibilities | 1900-01-13 | 1900-01-16
| Business/Engineering Specifications & Requirements | 1900-01-21 | 1900-01-23 | 3
| Concept Generation & Sketches | 1900-01-22 | 1900-01-27 | 6
| Down-Selection (Decision Matrix & HOQ) | 1900-01-27 | 1900-01-27 | 1
| Project Charter | 1900-01-19 | 1900-01-23 | 5
| Preliminary Materials List (BOM) & Budget | 1900-01-25 | 1900-01-28
| Economic Analysis | 1900-01-29 | 1900-01-31 | 3
| Initial Risk Register & FMEA | 1900-01-30 | 1900-02-02 | 4
| Assumptions & Free-Body Diagram | 1900-01-25 | 1900-01-30
| Preliminary CAD Model | 1900-01-27 | 1900-02-03
Critical Design Review - Design
| PDR Prototype (Cardboard Build Testing Probe & Soil Burrowing) | 1900-02-01 | 1900-02-05
| Force Modelling for Soil Burrowing | 1900-02-05 | 1900-02-09 | 5
| Gear & Rack Analysis (Pitch Diameter, Teeth) | 1900-02-08 | 1900-02-16 | 9
| Shaft Design (Material, Size, Key, Bearings) | 1900-02-09 | 1900-02-11 | 3
| Failure Mode Effects Analysis (FMEA) & Risk Re-Evaluation | 1900-02-14 | 1900-02-21 | 8
| Manufacutring & Assembly Plan (Sub-Assemblies, Machining Process) | 1900-02-21 | 1900-02-27
| Low-Risk Parts Order Placed | 1900-02-22 | 1900-03-04
| High-Level Testing Plan (Parts, Sub-Assemblies, Assembly) | 1900-03-02 | 1900-03-05
| Finalized Design & CAD Model | 1900-02-05 | 1900-03-07 | 31
Final Design Review
| High-Risk Parts Ordered | 1900-03-05 | 1900-03-15
| Manufacturing Drawings & Operation Sheets | 1900-03-07 | 1900-03-17
| Discussion with Machine Shop and Testing of Sensors/Arduino/Motors | 1900-03-12 | 1900-03-22 | 11
| Sub-Assembly 1 (Shaft-Gear-Rack System) Manufacturing | 1900-03-16 | 1900-03-31 | 16
| Sub-Assembly 2 (Outside Casing, Foot Pedals) Manufacturing | 1900-03-31 | 1900-04-07 | 8
| Sub-Assembly (Soil Testing Probe) Manufacturing | 1900-04-07 | 1900-04-12
| Put Subassemblies Together (Test Device) | 1900-04-12 | 1900-04-17
| Testing, Marketing, Poster, & Quality Check | 1900-04-17 | 1900-04-25 | 9
| Individual Component Testing, Sub-Assembly & Assembly Testing | 1900-03-07 | 1900-04-25 | 50
Formulas:
PDR = [PDR, row below]
Week 2 = [Week 2, row below]
Week 3 = [Week 3, row below]
Week 4 = [Week 4, row below]
CDR = [CDR, row below]
Week 6 = [Week 6, row below]
Week 7 = [Week 7, row below]
Week 8 = [Week 8, row below]
FDR = [FDR, row below]
Week 10 = [Week 10, row below]
Week 11 = [Week 11, row below]
Week 12 = [Week 12, row below]
Week 13 = [Week 13, row below]
Week 14 = [Week 14, row below]
Week 15 = [Week 15, row below]
Week 16 = [Week 16, row below]